## Drafting
Week	W38	W39	W40	W41	W42	W43	W44	W45	W46	W47	W48	W49	W50	W51
Month	September		October					November				December
Reference Date	19.09	26.09	03.10	10.10	17.10	24.10	31.10	07.11	14.11	21.11	28.11	05.12	12.12	19.12

Iterations
Sprint 1 (Inception) / - Write Problem Statement / - Write Project Plan / - Adapt Infrastructure
Sprint 2 (Elaboration) / - Create Use Cases / - Define Non-Functional-Requirements / - Academic Research / - Language Evaluation
Sprint 3 (Elaboration) / - Draft basic Architecture and Domain Model / - Bootstrap Project / - Prototype architectural critical components
Sprint 4 (Elaboration) / - Prototype architectural critical components / - Finalize Basic Architecture
Sprint 5 (Construction) / - Implement core / - set up testing infrastructure
Sprint 6 (Construction) / - Implement & Test core concepts
Sprint 7 (Transition) / - Finalize Implementation / - Prepare Release Documents / - Prepare Presentation
Sprint 9 (Transition) / - Final Release / - Project Presentation

Project Management
Kickoff
Sprint Planning
Supervision Meeting
Retrospective

Milestones
End of Inception
Project Plan completed
Requirements completed
Basic architecture fixed
Architecture architecture fixed
End of Elaboration
Core functionality implemented
Basic functionality implemented
Documentation completed
Final Release / Sumbission

Documents
Project Plan
Abstract
Management Summary
Poster
Presentation
Final Submission Document

## Overview
Kickoff					Sprint Planning
Sprint Planning		Sprint Planning			Sprint Planning			Sprint Planning			Sprint Planning			Sprint Planning					Sprint Planning

Sprint 1		Sprint 2			Sprint 3			Sprint 4			Sprint 5			Sprint 6			Sprint 7		Sprint 8

W38		W39	W40		W41	W42		W43	W44		W45	W46		W47	W48		W49		W50	W51

				Basic architecture / fixed					Final Release / / Sumbission
				Core functionality implemented
				Requirements completed					Documentation completed
				Retrospective 1
				Architecture architecture fixed					Basic functionality implemented
	Project Plan completed					Retrospective 1

## Sprint Details
Sprint	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Phase	Inception	Elaboration	Elaboration	Elaboration
Date	19.09.2017-25.09.2017	26.09.2017-09.10.2017	10.10.2017-23.10.2017	24.10.2017-06.11.2017
Milestones
Time Budget	34	68	68	68
Tasks	- Write Problem Statement / - Write Project Plan / - Adapt Infrastructure	- Create Use Cases / - Define Non-Functional-Requirements / - Academic Research / - Language Evaluation	- Draft basic Architecture and Domain Model / - Bootstrap Project / - Prototype architectural critical components	- Prototype architectural critical components / - Finalize Basic Architecture
Documents	- Problem Statement / - Project Plan	- Software Requirements Specification / - Research Report / - Section Language Evaluation	- Draft 1: Software Architecture Documentation	- Software Architecture Documentation

Sprint	Sprint 5	Sprint 6	Sprint 7	Sprint 8
Phase	Elaboration	Elaboration	Elaboration	“Transition”
Date	17.11.2017-20.11.2017	21.11.2017-04.12.2017	05.12.2017-11.12.2017	12.12.2017-22.12.2017
Milestones
Time Budget	68	68	34	68
Tasks	- Implement core / - set up testing infrastructure	- Implement core concepts / - Test core concepts	- Improve Code Quality & Documentation / - Exhaustive Testing	- Finalize Release Documents / - Prepare Presentation / - Project Presentation / - Final Release
Documents				- Poster / - Presentation / - Final Submission Document / - Management Summary / - Abstract

Total time budget: 478h + 2h for Kickoff (Before Sprint 1) + 2h Administration (vor SA)