## Report
Time Accounting

The study project has a time frame of 480 hours. In total, we spent 511.5 hours on the project which is 31.5 hours more than anticipated.

Time spent per Sprint
hours spent

We spent on average 34.1 hours per sprint which is close to the intended 34 hours. Due to additional work in other modules and personal appointments during Sprint 6, we pre-compensated the missing work in Sprint 5.

Time spent per Component

As intended, we spent the most time on the prototype. The management that includes project and sprint planning, standup and advisory meetings, as well as infrastructure tasks, took approximately a quarter of the project budget. The final submission document and the concept paper overlap because they are submitted together and can therefore not be isolated completely.

Estimated cost

Using the hourly wage from the module Software Engineering 2, the total project costs would be 44117 CHF in practice.

Time spent per Person

## worklogs
Issue Key	Issue summary	Hours	Work date	Username	Full name	Period	Account Key	Account Name	Account Lead	Account Category	Account Customer	Activity Name	Component	All Components	Version Name	Issue Type	Issue Status	Project Key	Project Name	Epic	Epic Link	Work Description	Parent Key	Reporter	External Hours	Billed Hours	Issue Original Estimate	Issue Remaining Estimate	Sprint
REDPRO-7	Set JIRA Project to public readable	0.25	2017-09-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-7		rzimmerm	0	0.25	0.25	0	Sprint 1
REDPRO-2	Sprint Planning Sprint 1	2	2017-09-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-2		rzimmerm	0	2	4	0	Sprint 1
REDPRO-2	Sprint Planning Sprint 1	2	2017-09-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Sprint planning		rzimmerm	0	2	4	0	Sprint 1
REDPRO-1	Project-Kickoff Meeting	0.5	2017-09-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting Minutes		rzimmerm	0	0.5	4	0	Preparation
REDPRO-1	Project-Kickoff Meeting	2	2017-09-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Discussion / Meeting		rzimmerm	0	2	4	0	Preparation
REDPRO-1	Project-Kickoff Meeting	2	2017-09-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Discussion		rzimmerm	0	2	4	0	Preparation
REDPRO-14	Write paragraph "Quality Measures" for Project Plan	1	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Working on issue REDPRO-14		rzimmerm	0	1	3	0.25	Sprint 1
REDPRO-3	Setup latexdiff in CI to be able to create diff-pdf for easier reviews	0.75	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-3		rzimmerm	0	0.75	1	0	Sprint 1
REDPRO-3	Setup latexdiff in CI to be able to create diff-pdf for easier reviews	0.25	2017-09-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-10	Write paragraph "Project Organization" for Project Plan	0.75	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Write paragraph		rzimmerm	0	0.75	2	1.25	Sprint 1
REDPRO-5	Setup proper backup solution	1.5	2017-09-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-5		rzimmerm	0	1.5	1	0	Sprint 1
REDPRO-11	Write paragraph "Project Workflow" for Project Plan	2.75	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Wrote first draft		rzimmerm	0	2.75	6	0.5	Sprint 1
REDPRO-9	Write paragraph "Project Overview" for Project Plan	0.75	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Working on issue REDPRO-9		rzimmerm	0	0.75	2	1.25	Sprint 1
REDPRO-16	Standup-Meetings Sprint 1	0.25	2017-09-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-16		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-16	Standup-Meetings Sprint 1	0.25	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Standup		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-3	Setup latexdiff in CI to be able to create diff-pdf for easier reviews	1.25	2017-09-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-3		rzimmerm	0	1.25	1	0	Sprint 1
REDPRO-5	Setup proper backup solution	0.25	2017-09-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Discuss realisation with rzimmerm		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-11	Write paragraph "Project Workflow" for Project Plan	0.25	2017-09-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Besprechung		rzimmerm	0	0.25	6	0.5	Sprint 1
REDPRO-5	Setup proper backup solution	0.5	2017-09-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Fix problem with cronjob & manual run		rzimmerm	0	0.5	1	0	Sprint 1
REDPRO-12	Write paragraph "Risk Management" for Project Plan	1.5	2017-09-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Create initial risk table		rzimmerm	0	1.5	3	0	Sprint 1
REDPRO-13	Write paragraph "Infrastructure" for Project Plan	1.25	2017-09-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Working on issue REDPRO-13		rzimmerm	0	1.25	2	0.5	Sprint 1
REDPRO-10	Write paragraph "Project Organization" for Project Plan	0.5	2017-09-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	components chapter and minor adjustments		rzimmerm	0	0.5	2	1.25	Sprint 1
REDPRO-11	Write paragraph "Project Workflow" for Project Plan	0.25	2017-09-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Besprechung		rzimmerm	0	0.25	6	0.5	Sprint 1
REDPRO-15	Kickoff Meeting with MeF	0.5	2017-09-22	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Writing Protocol		rzimmerm	0	0.5	3	0	Sprint 1
REDPRO-15	Kickoff Meeting with MeF	1	2017-09-22	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Sitzung		rzimmerm	0	1	3	0	Sprint 1
REDPRO-15	Kickoff Meeting with MeF	1	2017-09-22	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Meeting		rzimmerm	0	1	3	0	Sprint 1
REDPRO-6	Add license notice to the website.	0.25	2017-09-22	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Add License and emoji links		rzimmerm	0	0.25	0.25	0	Sprint 1
REDPRO-12	Write paragraph "Risk Management" for Project Plan	1.25	2017-09-22	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review and extend risks		rzimmerm	0	1.25	3	0	Sprint 1
REDPRO-12	Write paragraph "Risk Management" for Project Plan	0.5	2017-09-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Address issues		rzimmerm	0	0.5	3	0	Sprint 1
REDPRO-15	Kickoff Meeting with MeF	0.25	2017-09-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Write Agenda		rzimmerm	0	0.25	3	0	Sprint 1
REDPRO-15	Kickoff Meeting with MeF	0.25	2017-09-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Discussion on agenda		rzimmerm	0	0.25	3	0	Sprint 1
REDPRO-14	Write paragraph "Quality Measures" for Project Plan	1	2017-09-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review, minor adjustments and merge		rzimmerm	0	1	3	0.25	Sprint 1
REDPRO-10	Write paragraph "Project Organization" for Project Plan	0.25	2017-09-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review and merge		rzimmerm	0	0.25	2	1.25	Sprint 1
REDPRO-14	Write paragraph "Quality Measures" for Project Plan	0.75	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Working on issue REDPRO-14		rzimmerm	0	0.75	3	0.25	Sprint 1
REDPRO-11	Write paragraph "Project Workflow" for Project Plan	2.25	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Revise project plan		rzimmerm	0	2.25	6	0.5	Sprint 1
REDPRO-16	Standup-Meetings Sprint 1	0.25	2017-09-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-16		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-16	Standup-Meetings Sprint 1	0.25	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-16		rzimmerm	0	0.25	1	0	Sprint 1
REDPRO-12	Write paragraph "Risk Management" for Project Plan	0.5	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review / Language improvements.		rzimmerm	0	0.5	3	0	Sprint 1
REDPRO-10	Write paragraph "Project Organization" for Project Plan	0.25	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review / Language Improvements		rzimmerm	0	0.25	2	1.25	Sprint 1
REDPRO-13	Write paragraph "Infrastructure" for Project Plan	0.25	2017-09-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype		Essential Project Plan	Review		rzimmerm	0	0.25	2	0.5	Sprint 1
REDPRO-28	Tempo time reports public/user visibility	0.75	2017-09-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Support request		fhauser	0	0.75	2	0	Sprint 2
REDPRO-25	Academic Research	1	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-25		rzimmerm	0	1	9	0	Sprint 2
REDPRO-4	Setup latex template for the project plan and the final submission document	3	2017-09-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-4		rzimmerm	0	3	3	0	Sprint 2
REDPRO-22	Setup rough concept paper	1	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-22		rzimmerm	0	1	2.5	0.75	Sprint 2
REDPRO-19	Write "Scientific Writing Guide"	1	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-19		rzimmerm	0	1	3	0.75	Sprint 2
REDPRO-27	Project Plan review	0.75	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-27		rzimmerm	0	0.75	2.5	0	Sprint 2
REDPRO-27	Project Plan review	0.75	2017-09-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-27		rzimmerm	0	0.75	2.5	0	Sprint 2
REDPRO-18	Mini-Retro Sprint 1	0.25	2017-09-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-18		rzimmerm	0	0.25	0.5	0	Sprint 2
REDPRO-18	Mini-Retro Sprint 1	0.25	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-18		rzimmerm	0	0.25	0.5	0	Sprint 2
REDPRO-17	Sprint Planning Sprint 2	1	2017-09-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-17		rzimmerm	0	1	2	0	Sprint 2
REDPRO-17	Sprint Planning Sprint 2	1	2017-09-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-17		rzimmerm	0	1	2	0	Sprint 2
REDPRO-4	Setup latex template for the project plan and the final submission document	0.5	2017-09-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Configure Bamboo build		rzimmerm	0	0.5	3	0	Sprint 2
REDPRO-22	Setup rough concept paper	0.25	2017-09-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Review structure		rzimmerm	0	0.25	2.5	0.75	Sprint 2
REDPRO-19	Write "Scientific Writing Guide"	0.25	2017-09-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Review		rzimmerm	0	0.25	3	0.75	Sprint 2
REDPRO-25	Academic Research	0.75	2017-09-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Discussion		rzimmerm	0	0.75	9	0	Sprint 2
REDPRO-25	Academic Research	0.75	2017-09-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Discussion		rzimmerm	0	0.75	9	0	Sprint 2
REDPRO-25	Academic Research	3	2017-09-29	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-25		rzimmerm	0	3	9	0	Sprint 2
REDPRO-40	Weekly Meeting with Adviser	1	2017-09-29	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-40		rzimmerm	0	1	2.5	0	Sprint 2
REDPRO-40	Weekly Meeting with Adviser	1	2017-09-29	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting		rzimmerm	0	1	2.5	0	Sprint 2
REDPRO-25	Academic Research	3	2017-09-29	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Research + Discussion		rzimmerm	0	3	9	0	Sprint 2
REDPRO-28	Tempo time reports public/user visibility	1.25	2017-09-29	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Configure user self-registration and guest user		fhauser	0	1.25	2	0	Sprint 2
REDPRO-25	Academic Research	1	2017-09-30	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-25		rzimmerm	0	1	9	0	Sprint 2
REDPRO-25	Academic Research	1	2017-09-30	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-25		rzimmerm	0	1	9	0	Sprint 2
REDPRO-43	Infrastructure Updates Week 40	0.5	2017-09-30	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-43		fhauser	0	0.5	0.5	0	Sprint 2
REDPRO-42	Navigation fix and definition of done	1	2017-10-01	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-42		fhauser	0	1	1	0	Sprint 2
REDPRO-26	Brainstorm basic concept	0.5	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Summarise thoughts on design		rzimmerm	0	0.5	3	1.25	Sprint 2
REDPRO-24	Define quality of service attributes	2	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-24		rzimmerm	0	2	3	0.25	Sprint 2
REDPRO-27	Project Plan review	0.25	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			Increase risk		rzimmerm	0	0.25	2.5	0	Sprint 2
REDPRO-27	Project Plan review	0.25	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			Review		rzimmerm	0	0.25	2.5	0	Sprint 2
REDPRO-45	Sprint Planning Sprint 3	0.25	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review Issues		rzimmerm	0	0.25	2	0.75	Sprint 3
REDPRO-45	Sprint Planning Sprint 3	0.75	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-45		rzimmerm	0	0.75	2	0.75	Sprint 3
REDPRO-27	Project Plan review	0.25	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-27		rzimmerm	0	0.25	2.5	0	Sprint 2
REDPRO-40	Weekly Meeting with Adviser	0.25	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review minutes		rzimmerm	0	0.25	2.5	0	Sprint 2
REDPRO-41	Standup Meeting Sprint 2	0.5	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Standups Sprint 2		rzimmerm	0	0.5	1	0	Sprint 2
REDPRO-41	Standup Meeting Sprint 2	0.5	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-41		rzimmerm	0	0.5	1	0	Sprint 2
REDPRO-20	Retrospective 1	0.5	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-20		rzimmerm	0	0.5	1.5	0.5	Sprint 2
REDPRO-20	Retrospective 1	0.5	2017-10-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-20		rzimmerm	0	0.5	1.5	0.5	Sprint 2
REDPRO-24	Define quality of service attributes	0.5	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Write down basic roles & responsibilities		rzimmerm	0	0.5	3	0.25	Sprint 2
REDPRO-27	Project Plan review	0.5	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	REDPRO	Redbackup Prototype			implement remarks by MeF		rzimmerm	0	0.5	2.5	0	Sprint 2
REDPRO-40	Weekly Meeting with Adviser	0.5	2017-10-02	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Write Protocol		rzimmerm	0	0.5	2.5	0	Sprint 2
REDPRO-46	Elaborate and describe possible Scenarios	1	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review and merge		rzimmerm	0	1	8	0	Sprint 3
REDPRO-48	Carry out language evaluation	1	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Working on issue REDPRO-48		rzimmerm	0	1	7	0	Sprint 3
REDPRO-44	Research and Settle for a Case Tool	0.25	2017-10-03	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Concept Paper;Management		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Add draw.io to JIRA		rzimmerm	0	0.25	1	0.25	Sprint 3
REDPRO-50	Finalize Quality of Service Attributes / (N)FRs	2	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Concept Paper;Management		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Working on issue REDPRO-50		rzimmerm	0	2	5	0.75	Sprint 3
REDPRO-44	Research and Settle for a Case Tool	0.5	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Concept Paper;Management		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Working on issue REDPRO-44		rzimmerm	0	0.5	1	0.25	Sprint 3
REDPRO-45	Sprint Planning Sprint 3	0.25	2017-10-03	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-45		rzimmerm	0	0.25	2	0.75	Sprint 3
REDPRO-26	Brainstorm basic concept	0.5	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-26		rzimmerm	0	0.5	3	1.25	Sprint 2
REDPRO-26	Brainstorm basic concept	0.5	2017-10-03	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Discuss possibilities		rzimmerm	0	0.5	3	1.25	Sprint 2
REDPRO-24	Define quality of service attributes	0.25	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-24		rzimmerm	0	0.25	3	0.25	Sprint 2
REDPRO-26	Brainstorm basic concept	0.25	2017-10-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-1	Working on issue REDPRO-26		rzimmerm	0	0.25	3	1.25	Sprint 2
REDPRO-46	Elaborate and describe possible Scenarios	1.5	2017-10-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Identify more scenarios		rzimmerm	0	1.5	8	0	Sprint 3
REDPRO-48	Carry out language evaluation	0.25	2017-10-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Review Language Requirements		rzimmerm	0	0.25	7	0	Sprint 3
REDPRO-50	Finalize Quality of Service Attributes / (N)FRs	2	2017-10-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Concept Paper;Management		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review and group elements		rzimmerm	0	2	5	0.75	Sprint 3
REDPRO-49	Standup-Meetings Sprint 3	0.25	2017-10-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-49		rzimmerm	0	0.25	1	0	Sprint 3
REDPRO-49	Standup-Meetings Sprint 3	0.25	2017-10-06	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-49		rzimmerm	0	0.25	1	0	Sprint 3
REDPRO-46	Elaborate and describe possible Scenarios	3	2017-10-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Working on issue REDPRO-46		rzimmerm	0	3	8	0	Sprint 3
REDPRO-47	Draft testing section in concept paper	1.5	2017-10-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Working on issue REDPRO-47		rzimmerm	0	1.5	6	4.25	Sprint 3
REDPRO-46	Elaborate and describe possible Scenarios	0.75	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review and resolve merge conflicts		rzimmerm	0	0.75	8	0	Sprint 3
REDPRO-46	Elaborate and describe possible Scenarios	0.75	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review		rzimmerm	0	0.75	8	0	Sprint 3
REDPRO-48	Carry out language evaluation	1.75	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Working on issue REDPRO-48		rzimmerm	0	1.75	7	0	Sprint 3
REDPRO-48	Carry out language evaluation	0.5	2017-10-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Review		rzimmerm	0	0.5	7	0	Sprint 3
REDPRO-46	Elaborate and describe possible Scenarios	3	2017-10-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Write scenarios		rzimmerm	0	3	8	0	Sprint 3
REDPRO-48	Carry out language evaluation	2.5	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Working on issue REDPRO-48		rzimmerm	0	2.5	7	0	Sprint 3
REDPRO-48	Carry out language evaluation	3.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Working on issue REDPRO-48		rzimmerm	0	3.25	7	0	Sprint 3
REDPRO-57	Investigate why CI does not build certain branches	0.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-57		rzimmerm	0	0.25	0.5	0.25	Sprint 2
REDPRO-49	Standup-Meetings Sprint 3	0.25	2017-10-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-49		rzimmerm	0	0.25	1	0	Sprint 3
REDPRO-21	Mini-Retro Sprint 3	0.25	2017-10-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-21		rzimmerm	0	0.25	0.5	0	Sprint 3
REDPRO-21	Mini-Retro Sprint 3	0.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-21		rzimmerm	0	0.25	0.5	0	Sprint 3
REDPRO-49	Standup-Meetings Sprint 3	0.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-49		rzimmerm	0	0.25	1	0	Sprint 3
REDPRO-48	Carry out language evaluation	0.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype		Language-Evaluation	Working on issue REDPRO-48		rzimmerm	0	0.25	7	0	Sprint 3
REDPRO-50	Finalize Quality of Service Attributes / (N)FRs	0.25	2017-10-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Concept Paper;Management		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review & minor language improvements		rzimmerm	0	0.25	5	0.75	Sprint 3
REDPRO-56	Renew Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.5	2017-10-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-56		rzimmerm	0	0.5	0.5	0	Sprint 4
REDPRO-62	Refine Scenario description	4	2017-10-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-62		rzimmerm	0	4	6	0	Sprint 4
REDPRO-61	Meeting Week 4 with MeF	1.5	2017-10-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-61		rzimmerm	0	1.5	3	0	Sprint 4
REDPRO-61	Meeting Week 4 with MeF	1.5	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-61		rzimmerm	0	1.5	3	0	Sprint 4
REDPRO-62	Refine Scenario description	4	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-62		rzimmerm	0	4	6	0	Sprint 4
REDPRO-65	Get started with Rust and its network stack	0.75	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-65		rzimmerm	0	0.75	9	0	Sprint 4
REDPRO-61	Meeting Week 4 with MeF	0.25	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Prepare agenda		rzimmerm	0	0.25	3	0	Sprint 4
REDPRO-58	Sprint Planning Sprint 4	1.5	2017-10-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-58		rzimmerm	0	1.5	3	0	Sprint 4
REDPRO-58	Sprint Planning Sprint 4	1.5	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-58		rzimmerm	0	1.5	3	0	Sprint 4
REDPRO-47	Draft testing section in concept paper	0.25	2017-10-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-2	Review & Reseach alternatives (socks proxy)		rzimmerm	0	0.25	6	4.25	Sprint 3
REDPRO-61	Meeting Week 4 with MeF	0.75	2017-10-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Write minutes and create issues		rzimmerm	0	0.75	3	0	Sprint 4
REDPRO-61	Meeting Week 4 with MeF	0.25	2017-10-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review meeting minutes		rzimmerm	0	0.25	3	0	Sprint 4
REDPRO-62	Refine Scenario description	4	2017-10-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-62		rzimmerm	0	4	6	0	Sprint 4
REDPRO-62	Refine Scenario description	4	2017-10-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-62		rzimmerm	0	4	6	0	Sprint 4
REDPRO-65	Get started with Rust and its network stack	0.5	2017-10-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-65		rzimmerm	0	0.5	9	0	Sprint 4
REDPRO-59	Stadup-Meetings Sprint 4	0.25	2017-10-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-59		rzimmerm	0	0.25	1	0	Sprint 4
REDPRO-59	Stadup-Meetings Sprint 4	0.25	2017-10-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-59		rzimmerm	0	0.25	1	0	Sprint 4
REDPRO-65	Get started with Rust and its network stack	6	2017-10-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-65		rzimmerm	0	6	9	0	Sprint 4
REDPRO-65	Get started with Rust and its network stack	6	2017-10-15	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-65		rzimmerm	0	6	9	0	Sprint 4
REDPRO-62	Refine Scenario description	3	2017-10-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-62		rzimmerm	0	3	6	0	Sprint 4
REDPRO-64	Describe Data Structures relevant for Data transmission	4	2017-10-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	4	6	0	Sprint 4
REDPRO-63	Describe resposibilities of all components	4.25	2017-10-16	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-63		rzimmerm	0	4.25	3	0	Sprint 4
REDPRO-59	Stadup-Meetings Sprint 4	0.25	2017-10-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-59		rzimmerm	0	0.25	1	0	Sprint 4
REDPRO-59	Stadup-Meetings Sprint 4	0.25	2017-10-16	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-59		rzimmerm	0	0.25	1	0	Sprint 4
REDPRO-74	Review Specification	4	2017-10-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	4	8	0	Sprint 5
REDPRO-74	Review Specification	5.25	2017-10-17	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	5.25	8	0	Sprint 5
REDPRO-78	Sprint Planning Sprint 5	1	2017-10-17	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-78		rzimmerm	0	1	1.5	0	Sprint 5
REDPRO-78	Sprint Planning Sprint 5	1	2017-10-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-78		rzimmerm	0	1	1.5	0	Sprint 5
REDPRO-63	Describe resposibilities of all components	3	2017-10-17	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-3	Working on issue REDPRO-63		rzimmerm	0	3	3	0	Sprint 4
REDPRO-71	Clarify if git is an possible storage backend	0.5	2017-10-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-71		rzimmerm	0	0.5	0.5	0	Sprint 5
REDPRO-74	Review Specification	2	2017-10-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	2	8	0	Sprint 5
REDPRO-67	Remove examiner from the title sheet in the final submission document	0.25	2017-10-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-67		rzimmerm	0	0.25	0.25	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	2	2017-10-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	2	6	0	Sprint 5
REDPRO-68	Clarify that requirements are vague on purpose	0.25	2017-10-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-68		rzimmerm	0	0.25	0.5	0	Sprint 5
REDPRO-68	Clarify that requirements are vague on purpose	0.25	2017-10-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-68		rzimmerm	0	0.25	0.5	0	Sprint 5
REDPRO-74	Review Specification	0.25	2017-10-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	0.25	8	0	Sprint 5
REDPRO-74	Review Specification	0.25	2017-10-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	0.25	8	0	Sprint 5
REDPRO-74	Review Specification	0.5	2017-10-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-74		rzimmerm	0	0.5	8	0	Sprint 5
REDPRO-76	Meeting Week 5 with MeF	0.5	2017-10-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-76		rzimmerm	0	0.5	3	1.5	Sprint 5
REDPRO-69	Discuss possible strategies using the morphological box tequnique	0.25	2017-10-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-69		rzimmerm	0	0.25	4	1	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	0.5	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	review		rzimmerm	0	0.5	6	0	Sprint 5
REDPRO-69	Discuss possible strategies using the morphological box tequnique	0.5	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	fix issues		rzimmerm	0	0.5	4	1	Sprint 5
REDPRO-69	Discuss possible strategies using the morphological box tequnique	2	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-69		rzimmerm	0	2	4	1	Sprint 5
REDPRO-76	Meeting Week 5 with MeF	0.25	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting minutes		rzimmerm	0	0.25	3	1.5	Sprint 5
REDPRO-76	Meeting Week 5 with MeF	0.5	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting		rzimmerm	0	0.5	3	1.5	Sprint 5
REDPRO-70	Discuss possible Hash-Collisions	0.25	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	research		rzimmerm	0	0.25	1	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	4	2017-10-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	4	6	0	Sprint 5
REDPRO-77	Stadup-Meetings Sprint 5	0.25	2017-10-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-77		rzimmerm	0	0.25	1	0	Sprint 5
REDPRO-77	Stadup-Meetings Sprint 5	0.25	2017-10-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-77		rzimmerm	0	0.25	1	0	Sprint 5
REDPRO-79	Get familiar with Rust and its Network Stack	4	2017-10-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-79		rzimmerm	0	4	16.75	3.75	Sprint 5
REDPRO-76	Meeting Week 5 with MeF	0.25	2017-10-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review		rzimmerm	0	0.25	3	1.5	Sprint 5
REDPRO-69	Discuss possible strategies using the morphological box tequnique	0.25	2017-10-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-69		rzimmerm	0	0.25	4	1	Sprint 5
REDPRO-51	Infrastructure Updates Week 42	1.5	2017-10-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-51		fhauser	0	1.5	1	0	Sprint 5
REDPRO-79	Get familiar with Rust and its Network Stack	8	2017-10-22	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-79		rzimmerm	0	8	16.75	3.75	Sprint 5
REDPRO-70	Discuss possible Hash-Collisions	0.5	2017-10-23	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Review		rzimmerm	0	0.5	1	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	0.5	2017-10-23	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Review		rzimmerm	0	0.5	6	0	Sprint 5
REDPRO-72	Discuss the need of physical time in the system and potential risks of it	0.5	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	review		rzimmerm	0	0.5	2	0	Sprint 5
REDPRO-79	Get familiar with Rust and its Network Stack	1	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-79		rzimmerm	0	1	16.75	3.75	Sprint 5
REDPRO-72	Discuss the need of physical time in the system and potential risks of it	1.5	2017-10-23	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-72		rzimmerm	0	1.5	2	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	2.5	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	2.5	6	0	Sprint 5
REDPRO-70	Discuss possible Hash-Collisions	1.5	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-70		rzimmerm	0	1.5	1	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	1.5	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	1.5	6	0	Sprint 5
REDPRO-77	Stadup-Meetings Sprint 5	0.25	2017-10-23	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-77		rzimmerm	0	0.25	1	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	0.25	2017-10-23	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Working on issue REDPRO-64		rzimmerm	0	0.25	6	0	Sprint 5
REDPRO-64	Describe Data Structures relevant for Data transmission	0.25	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-4	Discuss Draft		rzimmerm	0	0.25	6	0	Sprint 5
REDPRO-77	Stadup-Meetings Sprint 5	0.25	2017-10-23	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-77		rzimmerm	0	0.25	1	0	Sprint 5
REDPRO-91	Continue to get familiar with Rust and its Network Stack	1.5	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-91		rzimmerm	0	1.5	6.75	0	Sprint 6
REDPRO-89	Bootstrap storage module	0.25	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-89		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-90	Bootstrap Node module	0.5	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-90		rzimmerm	0	0.5	0.5	0	Sprint 6
REDPRO-81	Configure latex glossaries	2	2017-10-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-5	Working on issue REDPRO-81		fhauser	0	2	2	0	Sprint 6
REDPRO-89	Bootstrap storage module	0.25	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core			rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-88	Bootstrap Management module	0.5	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-88		rzimmerm	0	0.5	0.5	0	Sprint 6
REDPRO-87	Bootstrap Client module	0.5	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-87		rzimmerm	0	0.5	0.5	0	Sprint 6
REDPRO-80	Tag Sprints 2 and 3	0.25	2017-10-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-80		rzimmerm	0	0.25	0.25	0	Sprint 6
REDPRO-85	Sprint Planning Sprint 6	0.75	2017-10-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-85		rzimmerm	0	0.75	2	0.5	Sprint 6
REDPRO-85	Sprint Planning Sprint 6	0.75	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-85		rzimmerm	0	0.75	2	0.5	Sprint 6
REDPRO-75	Mini-Retro Sprint 5	0.25	2017-10-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-75		rzimmerm	0	0.25	0.5	0	Sprint 5
REDPRO-75	Mini-Retro Sprint 5	0.25	2017-10-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-75		rzimmerm	0	0.25	0.5	0	Sprint 5
REDPRO-92	Write Glossary definition	0.75	2017-10-25	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-92		rzimmerm	0	0.75	2	0.25	Sprint 6
REDPRO-87	Bootstrap Client module	0.25	2017-10-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Add link to website		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-84	Improve diagrams in the specification	0.75	2017-10-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-5	Working on issue REDPRO-84		rzimmerm	0	0.75	1.5	0.75	Sprint 6
REDPRO-90	Bootstrap Node module	0.25	2017-10-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-90		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-89	Bootstrap storage module	0.25	2017-10-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-89		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-92	Write Glossary definition	0.5	2017-10-26	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Fix glossary and remove page numbers		rzimmerm	0	0.5	2	0.25	Sprint 6
REDPRO-66	Request Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.25	2017-10-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Write short request		fhauser	0	0.25	1	0	Sprint 7
REDPRO-92	Write Glossary definition	0.5	2017-10-26	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Review		rzimmerm	0	0.5	2	0.25	Sprint 6
REDPRO-91	Continue to get familiar with Rust and its Network Stack	1.25	2017-10-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-91		rzimmerm	0	1.25	6.75	0	Sprint 6
REDPRO-91	Continue to get familiar with Rust and its Network Stack	8.5	2017-10-30	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-91		rzimmerm	0	8.5	6.75	0	Sprint 6
REDPRO-97	Setup Diesel + Sqlite	3.25	2017-10-31	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-97		rzimmerm	0	3.25	8	0	Sprint 7
REDPRO-96	Prototype Tokio Communication between client and node	7.5	2017-10-31	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-96		rzimmerm	0	7.5	8	0	Sprint 7
REDPRO-66	Request Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.5	2017-10-31	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Send application		fhauser	0	0.5	1	0	Sprint 7
REDPRO-66	Request Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.5	2017-10-31	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-66		fhauser	0	0.5	1	0	Sprint 7
REDPRO-93	Sprint Planning Sprint 7	1	2017-10-31	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-93		rzimmerm	0	1	2	0	Sprint 7
REDPRO-93	Sprint Planning Sprint 7	1	2017-10-31	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-93		rzimmerm	0	1	2	0	Sprint 7
REDPRO-83	Send MeF the revised document when they are stable	0.25	2017-10-31	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-5	Working on issue REDPRO-83		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-83	Send MeF the revised document when they are stable	0.25	2017-10-31	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Draft-5	Working on issue REDPRO-83		rzimmerm	0	0.25	0.5	0	Sprint 6
REDPRO-96	Prototype Tokio Communication between client and node	2.25	2017-11-01	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-96		rzimmerm	0	2.25	8	0	Sprint 7
REDPRO-52	Infrastructure Updates Week 44	0.25	2017-11-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Update Backup server		fhauser	0	0.25	0.5	0	Sprint 7
REDPRO-66	Request Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.5	2017-11-02	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			- Try to fix issues as noted by atlassian / - Reply to request mail		fhauser	0	0.5	1	0	Sprint 7
REDPRO-97	Setup Diesel + Sqlite	5	2017-11-03	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Configure Diesel, Automigrations and r2d2 connection pooling		rzimmerm	0	5	8	0	Sprint 7
REDPRO-52	Infrastructure Updates Week 44	0.5	2017-11-03	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Install updates		fhauser	0	0.5	0.5	0	Sprint 7
REDPRO-96	Prototype Tokio Communication between client and node	3.5	2017-11-03	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	finalize		rzimmerm	0	3.5	8	0	Sprint 7
REDPRO-97	Setup Diesel + Sqlite	3	2017-11-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-97		rzimmerm	0	3	8	0	Sprint 7
REDPRO-97	Setup Diesel + Sqlite	4	2017-11-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-97		rzimmerm	0	4	8	0	Sprint 7
REDPRO-95	Finalize Testing Concept	5.5	2017-11-06	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-95		rzimmerm	0	5.5	5	0	Sprint 7
REDPRO-66	Request Licenses for JIRA/Bitbucket/Tempo/Crowd etc.	0.25	2017-11-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Configure Licenses		fhauser	0	0.25	1	0	Sprint 7
REDPRO-94	Standup Meetings Sprint 7	0.25	2017-11-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-94		rzimmerm	0	0.25	1	0.5	Sprint 7
REDPRO-94	Standup Meetings Sprint 7	0.25	2017-11-06	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-94		rzimmerm	0	0.25	1	0.5	Sprint 7
REDPRO-96	Prototype Tokio Communication between client and node	0.25	2017-11-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-96		rzimmerm	0	0.25	8	0	Sprint 7
REDPRO-96	Prototype Tokio Communication between client and node	0.25	2017-11-06	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	implement changes suggested in review		rzimmerm	0	0.25	8	0	Sprint 7
REDPRO-105	Database Abstraction Layer for Node	0.5	2017-11-07	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-105		fhauser	0	0.5	4	0	Sprint 8
REDPRO-100	Build extended docker image to generate junit and coverage reports	0.75	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-100		rzimmerm	0	0.75	2	0	Sprint 8
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	0.25	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	discussion		rzimmerm	0	0.25	4	0	Sprint 8
REDPRO-104	Setup new Build Server	2.5	2017-11-07	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Setup server		fhauser	0	2.5	2.5	0	Sprint 8
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	1	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	Working on issue REDPRO-98		rzimmerm	0	1	4	0	Sprint 8
REDPRO-100	Build extended docker image to generate junit and coverage reports	1.25	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-100		rzimmerm	0	1.25	2	0	Sprint 8
REDPRO-101	Sprint Planning Sprint 8	1	2017-11-07	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-101		rzimmerm	0	1	2	0	Sprint 8
REDPRO-101	Sprint Planning Sprint 8	1	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-101		rzimmerm	0	1	2	0	Sprint 8
REDPRO-95	Finalize Testing Concept	2.25	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-95		rzimmerm	0	2.25	5	0	Sprint 7
REDPRO-97	Setup Diesel + Sqlite	1	2017-11-07	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-97		rzimmerm	0	1	8	0	Sprint 7
REDPRO-97	Setup Diesel + Sqlite	0.25	2017-11-07	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-97		rzimmerm	0	0.25	8	0	Sprint 7
REDPRO-103	Meeting Week 8 with MeF	0.25	2017-11-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Preparation		rzimmerm	0	0.25	3	0	Sprint 8
REDPRO-103	Meeting Week 8 with MeF	0.25	2017-11-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Write minutes		rzimmerm	0	0.25	3	0	Sprint 8
REDPRO-103	Meeting Week 8 with MeF	1	2017-11-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-103		rzimmerm	0	1	3	0	Sprint 8
REDPRO-107	Implement basic version of storage component	1	2017-11-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-107		rzimmerm	0	1	2	0	Sprint 8
REDPRO-103	Meeting Week 8 with MeF	0.25	2017-11-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			preparation		rzimmerm	0	0.25	3	0	Sprint 8
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	1	2017-11-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	Working on issue REDPRO-98		rzimmerm	0	1	4	0	Sprint 8
REDPRO-100	Build extended docker image to generate junit and coverage reports	1.25	2017-11-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Review		rzimmerm	0	1.25	2	0	Sprint 8
REDPRO-103	Meeting Week 8 with MeF	0.25	2017-11-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-103		rzimmerm	0	0.25	3	0	Sprint 8
REDPRO-103	Meeting Week 8 with MeF	1	2017-11-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting		rzimmerm	0	1	3	0	Sprint 8
REDPRO-108	Database Abstraction Layer for Client	4.75	2017-11-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-108		rzimmerm	0	4.75	5	0	Sprint 8
REDPRO-105	Database Abstraction Layer for Node	7.5	2017-11-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-105		fhauser	0	7.5	4	0	Sprint 8
REDPRO-108	Database Abstraction Layer for Client	3.5	2017-11-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-108		rzimmerm	0	3.5	5	0	Sprint 8
REDPRO-105	Database Abstraction Layer for Node	1.25	2017-11-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Implement requested review changes		fhauser	0	1.25	4	0	Sprint 8
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	1.25	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	Working on issue REDPRO-98		rzimmerm	0	1.25	4	0	Sprint 8
REDPRO-100	Build extended docker image to generate junit and coverage reports	0.25	2017-11-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Review & Merge		rzimmerm	0	0.25	2	0	Sprint 8
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	1	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	Working on issue REDPRO-98		rzimmerm	0	1	4	0	Sprint 8
REDPRO-107	Implement basic version of storage component	2.5	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-107		rzimmerm	0	2.5	2	0	Sprint 8
REDPRO-102	Standup Meetings Sprint 8	0.25	2017-11-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-102		rzimmerm	0	0.25	1	0.5	Sprint 8
REDPRO-102	Standup Meetings Sprint 8	0.25	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-102		rzimmerm	0	0.25	1	0.5	Sprint 8
REDPRO-108	Database Abstraction Layer for Client	0.5	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	review		rzimmerm	0	0.5	5	0	Sprint 8
REDPRO-105	Database Abstraction Layer for Node	0.75	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Review		fhauser	0	0.75	4	0	Sprint 8
REDPRO-100	Build extended docker image to generate junit and coverage reports	0.5	2017-11-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Implement changes suggested by fhauser		rzimmerm	0	0.5	2	0	Sprint 8
REDPRO-110	Build Chunk Index on the Client	1	2017-11-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-110		rzimmerm	0	1	4.5	0	Sprint 9
REDPRO-111	Implement Request handling of get chunk states on the node	2.5	2017-11-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-111		rzimmerm	0	2.5	4.5	0	Sprint 9
REDPRO-114	Sprint Planning Sprint 9	1	2017-11-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-114		fhauser	0	1	2	0	Sprint 9
REDPRO-114	Sprint Planning Sprint 9	1	2017-11-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-114		fhauser	0	1	2	0	Sprint 9
REDPRO-98	Implement reasonable changes suggested by MeF in the final submission document	0.25	2017-11-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Concept Paper	Concept Paper	Concept Paper		Task	Done	REDPRO	Redbackup Prototype		Concept-Paper-Final	Review		rzimmerm	0	0.25	4	0	Sprint 8
REDPRO-106	Mini Retro Sprint 8	0.25	2017-11-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-106		rzimmerm	0	0.25	0.5	0	Sprint 8
REDPRO-106	Mini Retro Sprint 8	0.25	2017-11-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Redbackup Prototype	Other			Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-106		rzimmerm	0	0.25	0.5	0	Sprint 8
REDPRO-108	Database Abstraction Layer for Client	1	2017-11-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Review		rzimmerm	0	1	5	0	Sprint 8
REDPRO-107	Implement basic version of storage component	0.25	2017-11-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Review		rzimmerm	0	0.25	2	0	Sprint 8
REDPRO-111	Implement Request handling of get chunk states on the node	1	2017-11-16	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-111		rzimmerm	0	1	4.5	0	Sprint 9
REDPRO-117	Stand Up Meeting Sprint 9	0.25	2017-11-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-117		rzimmerm	0	0.25	1	0	Sprint 9
REDPRO-110	Build Chunk Index on the Client	2	2017-11-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-110		rzimmerm	0	2	4.5	0	Sprint 9
REDPRO-111	Implement Request handling of get chunk states on the node	2.5	2017-11-17	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-111		rzimmerm	0	2.5	4.5	0	Sprint 9
REDPRO-117	Stand Up Meeting Sprint 9	0.25	2017-11-17	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-117		rzimmerm	0	0.25	1	0	Sprint 9
REDPRO-53	Infrastructure Updates Week 46	1	2017-11-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-53		fhauser	0	1	1	0	Sprint 9
REDPRO-117	Stand Up Meeting Sprint 9	0.25	2017-11-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-117		rzimmerm	0	0.25	1	0	Sprint 9
REDPRO-110	Build Chunk Index on the Client	1	2017-11-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-110		rzimmerm	0	1	4.5	0	Sprint 9
REDPRO-115	Plan documentation structure and final documentation sprints	1.5	2017-11-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-115		fhauser	0	1.5	1.5	0	Sprint 9
REDPRO-112	Implement Request handling of post chunks on the node	0.75	2017-11-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-112		rzimmerm	0	0.75	4.5	0	Sprint 9
REDPRO-116	Highlight relevant issues in the requirements	0.5	2017-11-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-116		rzimmerm	0	0.5	0.5	0	Sprint 9
REDPRO-112	Implement Request handling of post chunks on the node	4	2017-11-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-112		rzimmerm	0	4	4.5	0	Sprint 9
REDPRO-117	Stand Up Meeting Sprint 9	0.25	2017-11-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-117		rzimmerm	0	0.25	1	0	Sprint 9
REDPRO-110	Build Chunk Index on the Client	4	2017-11-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-110		rzimmerm	0	4	4.5	0	Sprint 9
REDPRO-147	Refactor Backup Process on the Client	1	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-147		rzimmerm	0	1	3.5	0	Sprint 10
REDPRO-125	Implement get root handles on the node	1	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-125		rzimmerm	0	1	3	1.75	Sprint 10
REDPRO-126	Implement get chunks on the node	0.25	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-126		rzimmerm	0	0.25	2	0.75	Sprint 10
REDPRO-147	Refactor Backup Process on the Client	0.75	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-147		rzimmerm	0	0.75	3.5	0	Sprint 10
REDPRO-126	Implement get chunks on the node	1	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-126		rzimmerm	0	1	2	0.75	Sprint 10
REDPRO-133	Sprint Planning Sprint 10	0.5	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-133		rzimmerm	0	0.5	2	0.5	Sprint 10
REDPRO-131	Meeting Week 10 with MeF	1	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-131		rzimmerm	0	1	2.5	0	Sprint 10
REDPRO-133	Sprint Planning Sprint 10	1	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-133		rzimmerm	0	1	2	0.5	Sprint 10
REDPRO-131	Meeting Week 10 with MeF	0.5	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Preparation & Protocol		rzimmerm	0	0.5	2.5	0	Sprint 10
REDPRO-131	Meeting Week 10 with MeF	1	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Meeting		rzimmerm	0	1	2.5	0	Sprint 10
REDPRO-113	Implement backup process on the client	5	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-113		rzimmerm	0	5	4.5	0	Sprint 9
REDPRO-116	Highlight relevant issues in the requirements	0.25	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-116		rzimmerm	0	0.25	0.5	0	Sprint 9
REDPRO-115	Plan documentation structure and final documentation sprints	0.25	2017-11-21	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		fhauser	0	0.25	1.5	0	Sprint 9
REDPRO-115	Plan documentation structure and final documentation sprints	1	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-115		fhauser	0	1	1.5	0	Sprint 9
REDPRO-113	Implement backup process on the client	2	2017-11-21	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Core	Working on issue REDPRO-113		rzimmerm	0	2	4.5	0	Sprint 9
REDPRO-125	Implement get root handles on the node	0.25	2017-11-22	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Review		rzimmerm	0	0.25	3	1.75	Sprint 10
REDPRO-147	Refactor Backup Process on the Client	4	2017-11-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-147		rzimmerm	0	4	3.5	0	Sprint 10
REDPRO-132	Standup Meetings Sprint 10	0.25	2017-11-24	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-132		rzimmerm	0	0.25	1	0	Sprint 10
REDPRO-132	Standup Meetings Sprint 10	0.25	2017-11-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-132		rzimmerm	0	0.25	1	0	Sprint 10
REDPRO-148	Enable backup of large files	3.75	2017-11-24	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-148		rzimmerm	0	3.75	5	0	Sprint 10
REDPRO-148	Enable backup of large files	0.5	2017-11-25	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Review and test issue		rzimmerm	0	0.5	5	0	Sprint 10
REDPRO-152	Sprint Planning Sprint 11	0.5	2017-11-27	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			preparation		rzimmerm	0	0.5	2	0.75	Sprint 11
REDPRO-132	Standup Meetings Sprint 10	0.25	2017-11-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-132		rzimmerm	0	0.25	1	0	Sprint 10
REDPRO-121	Implement Restore process on the client	1.5	2017-11-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Clean up and write tests		rzimmerm	0	1.5	5	0	Sprint 10
REDPRO-147	Refactor Backup Process on the Client	1	2017-11-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Implement refactorings		rzimmerm	0	1	3.5	0	Sprint 10
REDPRO-132	Standup Meetings Sprint 10	0.25	2017-11-27	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-132		rzimmerm	0	0.25	1	0	Sprint 10
REDPRO-148	Enable backup of large files	0.25	2017-11-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-148		rzimmerm	0	0.25	5	0	Sprint 10
REDPRO-148	Enable backup of large files	0.5	2017-11-27	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-148		rzimmerm	0	0.5	5	0	Sprint 10
REDPRO-147	Refactor Backup Process on the Client	1	2017-11-27	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Review		rzimmerm	0	1	3.5	0	Sprint 10
REDPRO-121	Implement Restore process on the client	5	2017-11-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-121		rzimmerm	0	5	5	0	Sprint 10
REDPRO-122	Implement a mechanism to ignore files during backup creation	0.5	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Implement tests and CLI-help		rzimmerm	0	0.5	3	0	Sprint 11
REDPRO-120	Show current process of a backup/restore process in percent, time spent and remaining estimate	3	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-120		rzimmerm	0	3	3	0	Sprint 11
REDPRO-122	Implement a mechanism to ignore files during backup creation	2	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-122		rzimmerm	0	2	3	0	Sprint 11
REDPRO-118	Implement integrity checks on the node	1.5	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-118		rzimmerm	0	1.5	3.5	0	Sprint 11
REDPRO-123	Ensure all interaction and side effects are logged appropriately	2.25	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-123		rzimmerm	0	2.25	2	0	Sprint 11
REDPRO-54	Infrastructure Updates Week 48	0.5	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-54		fhauser	0	0.5	0.5	0	Sprint 11
REDPRO-152	Sprint Planning Sprint 11	0.5	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-152		rzimmerm	0	0.5	2	0.75	Sprint 11
REDPRO-152	Sprint Planning Sprint 11	0.25	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-152		rzimmerm	0	0.25	2	0.75	Sprint 11
REDPRO-134	Retrospective 3	1	2017-11-28	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-134		rzimmerm	0	1	2	0	Sprint 10
REDPRO-134	Retrospective 3	1	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-134		rzimmerm	0	1	2	0	Sprint 10
REDPRO-121	Implement Restore process on the client	0.5	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	review		rzimmerm	0	0.5	5	0	Sprint 10
REDPRO-119	Implement replication process on nodes	4.5	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-119		rzimmerm	0	4.5	5	0	Sprint 11
REDPRO-118	Implement integrity checks on the node	2	2017-11-28	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-118		rzimmerm	0	2	3.5	0	Sprint 11
REDPRO-118	Implement integrity checks on the node	0.25	2017-11-29	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-118		rzimmerm	0	0.25	3.5	0	Sprint 11
REDPRO-119	Implement replication process on nodes	0.5	2017-11-29	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-119		rzimmerm	0	0.5	5	0	Sprint 11
REDPRO-151	Integration Tests with Docker	2	2017-11-30	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-151		fhauser	0	2	5	0	Sprint 11
REDPRO-122	Implement a mechanism to ignore files during backup creation	0.25	2017-11-30	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	review		rzimmerm	0	0.25	3	0	Sprint 11
REDPRO-120	Show current process of a backup/restore process in percent, time spent and remaining estimate	0.5	2017-11-30	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Implement changes from review		rzimmerm	0	0.5	3	0	Sprint 11
REDPRO-151	Integration Tests with Docker	3	2017-12-01	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-151		fhauser	0	3	5	0	Sprint 11
REDPRO-151	Integration Tests with Docker	2	2017-12-01	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing			fhauser	0	2	5	0	Sprint 11
REDPRO-119	Implement replication process on nodes	0.5	2017-12-04	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Finish review and merge		rzimmerm	0	0.5	5	0	Sprint 11
REDPRO-153	Standup Meetings Sprint 11	0.25	2017-12-04	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-153		rzimmerm	0	0.25	1	0	Sprint 11
REDPRO-159	Add signed and scanned task description to the final sumbission document	0.25	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	latex recherche		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-128	Write Abstract	0.25	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.25	2	0.5	Sprint 12
REDPRO-177	Clarify installation instructions	0.75	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-177		rzimmerm	0	0.75	0.5	0	Sprint 12
REDPRO-128	Write Abstract	1	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-128		rzimmerm	0	1	2	0.5	Sprint 12
REDPRO-150	Check if chunk content was already sent to node	0.5	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-150		fhauser	0	0.5	0.5	0	Sprint 12
REDPRO-181	Complete Integration Tests	4.75	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-181		fhauser	0	4.75	3	0	Sprint 12
REDPRO-156	Use SQLITE in WAL-Mode	0.25	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype			Remove WAL from client		fhauser	0	0.25	1	0	Sprint 12
REDPRO-156	Use SQLITE in WAL-Mode	0.75	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-156		fhauser	0	0.75	1	0	Sprint 12
REDPRO-160	Sprint Planning Sprint 12	0.75	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-160		rzimmerm	0	0.75	3	0	Sprint 12
REDPRO-122	Implement a mechanism to ignore files during backup creation	0.5	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-122		rzimmerm	0	0.5	3	0	Sprint 11
REDPRO-160	Sprint Planning Sprint 12	0.5	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-160		rzimmerm	0	0.5	3	0	Sprint 12
REDPRO-153	Standup Meetings Sprint 11	0.25	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-153		rzimmerm	0	0.25	1	0	Sprint 11
REDPRO-153	Standup Meetings Sprint 11	0.25	2017-12-05	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-153		rzimmerm	0	0.25	1	0	Sprint 11
REDPRO-160	Sprint Planning Sprint 12	2	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			planning		rzimmerm	0	2	3	0	Sprint 12
REDPRO-153	Standup Meetings Sprint 11	0.25	2017-12-05	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-153		rzimmerm	0	0.25	1	0	Sprint 11
REDPRO-181	Complete Integration Tests	0.5	2017-12-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Review		fhauser	0	0.5	3	0	Sprint 12
REDPRO-128	Write Abstract	0.25	2017-12-06	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-128		rzimmerm	0	0.25	2	0.5	Sprint 12
REDPRO-129	Finalzie Acknowledgements in the final submission document	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-129		rzimmerm	0	0.25	0.5	0.25	Sprint 12
REDPRO-146	Create an updated version of the project plan that matches the actual project course	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.25	1.5	0	Sprint 12
REDPRO-159	Add signed and scanned task description to the final sumbission document	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-159		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-169	Add Project Plan as attachment to the final submission document	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-169		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-168	Add usage rights to the final submission document (license)	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-177	Clarify installation instructions	0.5	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.5	0.5	0	Sprint 12
REDPRO-158	Performance Testing	2	2017-12-08	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-158		rzimmerm	0	2	2	0	Sprint 12
REDPRO-150	Check if chunk content was already sent to node	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Review		fhauser	0	0.25	0.5	0	Sprint 12
REDPRO-181	Complete Integration Tests	1.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Fix build and review		fhauser	0	1.25	3	0	Sprint 12
REDPRO-162	Standup Meetings Sprint 12	0.25	2017-12-08	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-162		rzimmerm	0	0.25	1	0	Sprint 12
REDPRO-162	Standup Meetings Sprint 12	0.25	2017-12-08	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-162		rzimmerm	0	0.25	1	0	Sprint 12
REDPRO-146	Create an updated version of the project plan that matches the actual project course	1	2017-12-08	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-146		rzimmerm	0	1	1.5	0	Sprint 12
REDPRO-169	Add Project Plan as attachment to the final submission document	0.25	2017-12-08	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-169		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-168	Add usage rights to the final submission document (license)	0.5	2017-12-08	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-168		rzimmerm	0	0.5	0.5	0	Sprint 12
REDPRO-158	Performance Testing	2	2017-12-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-158		rzimmerm	0	2	2	0	Sprint 12
REDPRO-155	Create detailed architecture overview	1.25	2017-12-09	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	1.25	2	0	Sprint 12
REDPRO-179	Document review guidelines (and that they must apply to every PR)	0.5	2017-12-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-179		rzimmerm	0	0.5	0.5	0	Sprint 12
REDPRO-156	Use SQLITE in WAL-Mode	2.5	2017-12-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype			Debugging		fhauser	0	2.5	1	0	Sprint 12
REDPRO-145	Write management summary	1.5	2017-12-09	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-145		rzimmerm	0	1.5	1.5	0	Sprint 12
REDPRO-145	Write management summary	0.5	2017-12-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-145		rzimmerm	0	0.5	1.5	0	Sprint 12
REDPRO-179	Document review guidelines (and that they must apply to every PR)	0.25	2017-12-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-179		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-154	Improve Code Documentation and Formatting	1.75	2017-12-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-154		fhauser	0	1.75	2	0	Sprint 12
REDPRO-158	Performance Testing	0.5	2017-12-10	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Review		rzimmerm	0	0.5	2	0	Sprint 12
REDPRO-145	Write management summary	0.25	2017-12-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-145		rzimmerm	0	0.25	1.5	0	Sprint 12
REDPRO-155	Create detailed architecture overview	1	2017-12-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	1	2	0	Sprint 12
REDPRO-155	Create detailed architecture overview	1.5	2017-12-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	1.5	2	0	Sprint 12
REDPRO-179	Document review guidelines (and that they must apply to every PR)	0.25	2017-12-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.25	0.5	0	Sprint 12
REDPRO-158	Performance Testing	0.5	2017-12-10	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Testing	Working on issue REDPRO-158		rzimmerm	0	0.5	2	0	Sprint 12
REDPRO-155	Create detailed architecture overview	2.5	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	2.5	2	0	Sprint 12
REDPRO-176	Document test results including test coverage (integration tests?)	1.25	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	1.25	1	0	Sprint 12
REDPRO-176	Document test results including test coverage (integration tests?)	0.75	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.75	1	0	Sprint 12
REDPRO-145	Write management summary	0.25	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-145		rzimmerm	0	0.25	1.5	0	Sprint 12
REDPRO-155	Create detailed architecture overview	3	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	3	2	0	Sprint 12
REDPRO-146	Create an updated version of the project plan that matches the actual project course	0.25	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-146		rzimmerm	0	0.25	1.5	0	Sprint 12
REDPRO-155	Create detailed architecture overview	0.25	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Read trough report		rzimmerm	0	0.25	2	0	Sprint 12
REDPRO-146	Create an updated version of the project plan that matches the actual project course	0.5	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-146		rzimmerm	0	0.5	1.5	0	Sprint 12
REDPRO-145	Write management summary	0.5	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-145		rzimmerm	0	0.5	1.5	0	Sprint 12
REDPRO-155	Create detailed architecture overview	2.5	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	2.5	2	0	Sprint 12
REDPRO-162	Standup Meetings Sprint 12	0.25	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-162		rzimmerm	0	0.25	1	0	Sprint 12
REDPRO-162	Standup Meetings Sprint 12	0.25	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-162		rzimmerm	0	0.25	1	0	Sprint 12
REDPRO-154	Improve Code Documentation and Formatting	0.25	2017-12-11	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	Working on issue REDPRO-154		fhauser	0	0.25	2	0	Sprint 12
REDPRO-154	Improve Code Documentation and Formatting	0.5	2017-12-11	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Prototype	Prototype	Prototype		Task	Done	REDPRO	Redbackup Prototype		Prototype-Basic	review		fhauser	0	0.5	2	0	Sprint 12
REDPRO-136	Write Section "Goals and Tasks" in Introduction	1.75	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-136		rzimmerm	0	1.75	1	0	Sprint 13
REDPRO-135	Write Section "Motivation" in Introduction	2	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-135		rzimmerm	0	2	1	0	Sprint 13
REDPRO-138	Write Section "Restore" in Our Approach	1	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-138		rzimmerm	0	1	2	0	Sprint 13
REDPRO-138	Write Section "Restore" in Our Approach	0.5	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.5	2	0	Sprint 13
REDPRO-139	Write Section "Backup" in Our Approach	0.5	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.5	2	0.5	Sprint 13
REDPRO-138	Write Section "Restore" in Our Approach	1	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-138		rzimmerm	0	1	2	0	Sprint 13
REDPRO-173	Correct and Submit Abstract to MeF	0.25	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-173		rzimmerm	0	0.25	1	0	Sprint 13
REDPRO-139	Write Section "Backup" in Our Approach	1	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-139		rzimmerm	0	1	2	0.5	Sprint 13
REDPRO-135	Write Section "Motivation" in Introduction	0.5	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-135		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-180	Supervision Meeting with MeF	0.25	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Review		rzimmerm	0	0.25	2.5	1	Sprint 13
REDPRO-173	Correct and Submit Abstract to MeF	0.75	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype			update abstract		rzimmerm	0	0.75	1	0	Sprint 13
REDPRO-180	Supervision Meeting with MeF	0.25	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			finalize meeting minutes		rzimmerm	0	0.25	2.5	1	Sprint 13
REDPRO-180	Supervision Meeting with MeF	0.5	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-180		rzimmerm	0	0.5	2.5	1	Sprint 13
REDPRO-161	Sprint Planning Sprint 13	0.25	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-161		rzimmerm	0	0.25	0.5	0	Sprint 13
REDPRO-180	Supervision Meeting with MeF	0.5	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-180		rzimmerm	0	0.5	2.5	1	Sprint 13
REDPRO-161	Sprint Planning Sprint 13	0.25	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-161		rzimmerm	0	0.25	0.5	0	Sprint 13
REDPRO-99	Send Documents for Language Review	0.25	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-99		fhauser	0	0.25	0.25	0	Sprint 12
REDPRO-155	Create detailed architecture overview	1	2017-12-12	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-155		rzimmerm	0	1	2	0	Sprint 12
REDPRO-176	Document test results including test coverage (integration tests?)	3	2017-12-12	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Improve		rzimmerm	0	3	1	0	Sprint 12
REDPRO-135	Write Section "Motivation" in Introduction	0.5	2017-12-13	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-166	Write personal report rzimmerm	0.25	2017-12-13	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.25	1	0.25	Sprint 13
REDPRO-167	Write personal report fhauser	0.5	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-167		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-183	Note that encryption was left out on purpose	0.25	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-183		rzimmerm	0	0.25	1	0.5	Sprint 13
REDPRO-165	Finalise Glossary and Bibliography	0.5	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-165		rzimmerm	0	0.5	0.5	0	Sprint 13
REDPRO-136	Write Section "Goals and Tasks" in Introduction	0.75	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-136		rzimmerm	0	0.75	1	0	Sprint 13
REDPRO-163	Standup Meetings Sprint 13	0.25	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-163		rzimmerm	0	0.25	0.5	0	Sprint 13
REDPRO-163	Standup Meetings Sprint 13	0.25	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-163		rzimmerm	0	0.25	0.5	0	Sprint 13
REDPRO-182	Discuss performance problems and reference them from our approach	0.5	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-182		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-183	Note that encryption was left out on purpose	0.25	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-183		rzimmerm	0	0.25	1	0.5	Sprint 13
REDPRO-165	Finalise Glossary and Bibliography	1	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-165		rzimmerm	0	1	0.5	0	Sprint 13
REDPRO-135	Write Section "Motivation" in Introduction	0.25	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-135		rzimmerm	0	0.25	1	0	Sprint 13
REDPRO-135	Write Section "Motivation" in Introduction	1	2017-12-14	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-135		rzimmerm	0	1	1	0	Sprint 13
REDPRO-136	Write Section "Goals and Tasks" in Introduction	0.5	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-166	Write personal report rzimmerm	0.5	2017-12-14	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-166		rzimmerm	0	0.5	1	0.25	Sprint 13
REDPRO-165	Finalise Glossary and Bibliography	0.25	2017-12-15	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-165		rzimmerm	0	0.25	0.5	0	Sprint 13
REDPRO-142	Write Section "Future Work" in Discussion and Conclusion	0.5	2017-12-15	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-142		rzimmerm	0	0.5	1.5	0	Sprint 13
REDPRO-136	Write Section "Goals and Tasks" in Introduction	0.25	2017-12-15	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-136		rzimmerm	0	0.25	1	0	Sprint 13
REDPRO-140	Write Section "Achieved Results" in Discussion and Conclusion	2	2017-12-15	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-140		rzimmerm	0	2	1	0	Sprint 13
REDPRO-182	Discuss performance problems and reference them from our approach	1	2017-12-15	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-182		rzimmerm	0	1	1	0	Sprint 13
REDPRO-141	Write Section "Lessons Learned" in Discussion and Conclusion	2	2017-12-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-141		rzimmerm	0	2	1	0	Sprint 13
REDPRO-167	Write personal report fhauser	0.75	2017-12-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-167		rzimmerm	0	0.75	1	0	Sprint 13
REDPRO-141	Write Section "Lessons Learned" in Discussion and Conclusion	0.25	2017-12-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-141		rzimmerm	0	0.25	1	0	Sprint 13
REDPRO-137	Write Section "State of the Art in Introduction	4	2017-12-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-137		rzimmerm	0	4	1	0	Sprint 13
REDPRO-141	Write Section "Lessons Learned" in Discussion and Conclusion	3	2017-12-17	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-141		rzimmerm	0	3	1	0	Sprint 13
REDPRO-143	Write Section "Conclusion" in Discussion and Conclusion	1.25	2017-12-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-143		rzimmerm	0	1.25	1	0	Sprint 13
REDPRO-137	Write Section "State of the Art in Introduction	0.5	2017-12-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Rebase		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-137	Write Section "State of the Art in Introduction	0.5	2017-12-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-137		rzimmerm	0	0.5	1	0	Sprint 13
REDPRO-182	Discuss performance problems and reference them from our approach	1.25	2017-12-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-182		rzimmerm	0	1.25	1	0	Sprint 13
REDPRO-142	Write Section "Future Work" in Discussion and Conclusion	0.5	2017-12-18	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Review		rzimmerm	0	0.5	1.5	0	Sprint 13
REDPRO-127	Create Poster	2.5	2017-12-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-127		rzimmerm	0	2.5	3	0	Sprint 14
REDPRO-141	Write Section "Lessons Learned" in Discussion and Conclusion	0.25	2017-12-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.25	1	0	Sprint 13
REDPRO-171	Burn CD containing all documents including the project website, jira export etc.	0.5	2017-12-18	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	In Progress	REDPRO	Redbackup Prototype		Submission	research		rzimmerm	0	0.5	1.5	0	Sprint 14
REDPRO-170	Print and bind the final submission document	2	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Review	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-170		rzimmerm	0	2	2	0	Sprint 14
REDPRO-174	Submit Abstract on abstract.hsr.ch	0.5	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-174		rzimmerm	0	0.5	0.5	0	Sprint 14
REDPRO-187	Clarify why we have many Intentions	0.5	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-187		fhauser	0	0.5	1	0.5	Sprint 14
REDPRO-188	Explicitly note fulfilled Requirements	0.5	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-188		fhauser	0	0.5	1	0.5	Sprint 14
REDPRO-184	Read and correct the final submission document	2	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-184		rzimmerm	0	2	10	0	Sprint 14
REDPRO-185	Second Review Glossary and Bibliography	0.5	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-185		fhauser	0	0.5	0.5	0	Sprint 14
REDPRO-186	Add CLI to attachments	0.5	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-186		fhauser	0	0.5	0.5	0	Sprint 14
REDPRO-144	Prepare final Presentation	1	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-144		rzimmerm	0	1	2	0	Sprint 14
REDPRO-127	Create Poster	0.5	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-127		rzimmerm	0	0.5	3	0	Sprint 14
REDPRO-178	Bring documents to MeF	0.25	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-178		rzimmerm	0	0.25	0.25	0	Sprint 14
REDPRO-127	Create Poster	0.25	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-127		rzimmerm	0	0.25	3	0	Sprint 14
REDPRO-144	Prepare final Presentation	1	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-144		rzimmerm	0	1	2	0	Sprint 14
REDPRO-164	Sprint Planning Sprint 14	0.25	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-164		rzimmerm	0	0.25	0.5	0	Sprint 14
REDPRO-55	Infrastructure Updates Week 50	0.5	2017-12-19	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-55		fhauser	0	0.5	0.5	0	Sprint 14
REDPRO-164	Sprint Planning Sprint 14	0.25	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	REDPRO	Redbackup Prototype			Working on issue REDPRO-164		rzimmerm	0	0.25	0.5	0	Sprint 14
REDPRO-142	Write Section "Future Work" in Discussion and Conclusion	0.5	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Documentation	review		rzimmerm	0	0.5	1.5	0	Sprint 13
REDPRO-184	Read and correct the final submission document	8	2017-12-19	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-184		rzimmerm	0	8	10	0	Sprint 14
REDPRO-149	Time accounting	0.25	2017-12-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	In Progress	REDPRO	Redbackup Prototype		Documentation	finalise		rzimmerm	0	0.25	1.5	0	Sprint 14
REDPRO-175	Submit final submission document + Abstract on https://archiv-i.hsr.ch/	0.5	2017-12-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Review	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-175		rzimmerm	0	0.5	0.5	0	Sprint 14
REDPRO-171	Burn CD containing all documents including the project website, jira export etc.	2	2017-12-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	In Progress	REDPRO	Redbackup Prototype		Submission	Working on issue REDPRO-171		rzimmerm	0	2	1.5	0	Sprint 14
REDPRO-149	Time accounting	2	2017-12-20	rzimmerm	Raphael Zimmermann		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	In Progress	REDPRO	Redbackup Prototype		Documentation	Working on issue REDPRO-149		rzimmerm	0	2	1.5	0	Sprint 14

## pivot_sprints
Sprint	Sum - Hours	Soll
Preparation	4.5	0
Sprint 1	29	34
Sprint 2	34.75	34
Sprint 3	29	34
Sprint 4	52.25	34
Sprint 5	51.75	34
Sprint 6	20.75	34
Sprint 7	43.25	34
Sprint 8	40.75	34
Sprint 9	33.25	34
Sprint 10	29.25	34
Sprint 11	28	34
Sprint 12	51.5	34
Sprint 13	37.25	34
Sprint 14	26.25	34
(empty)
Total Result	511.5

Sprint Average:	34.1

## pivot_components
Component	Sum - Hours		Kosten		Kosten pro Personentag	CHF 690.00
Concept Paper	96.5	18.87%	CHF 8'323.13		Kosten pro Arbeitsstunde	CHF 86.25
Final Submission Document	79.75	15.59%	CHF 6'878.44		Quelle: SE2 aufwandschaetzung.pdf, F45, Dr. Daniel Keller
Management	141.5	27.66%	CHF 12'204.38
Other	14	2.74%	CHF 1'207.50
Project Plan	18.75	3.67%	CHF 1'617.19
Prototype	161	31.48%	CHF 13'886.25
(empty)			CHF 44'116.88
Total Result	511.5

## pivot_users
Full name	Sum - Hours
Fabian Hauser	249.75
Raphael Zimmermann	261.75
(empty)
Total Result	511.5