## Drafting
Week	W38	W39	W40	W41	W42	W43	W44	W45	W46	W47	W48	W49	W50	W51
Month	September		October					November				December
Reference Date	19.09	26.09	03.10	10.10	17.10	24.10	31.10	07.11	14.11	21.11	28.11	05.12	12.12	19.12

Iterations
Sprint 1 (Inception) / - Write Problem Statement / - Write Project Plan / - Adapt Infrastructure
Sprint 2 (Elaboration) / - Create Use Cases / - Define Non-Functional-Requirements / - Academic Research / - Language Evaluation
Sprint 3 (Elaboration) / - Draft basic Architecture and Domain Model / - Bootstrap Project / - Prototype architectural critical components
Sprint 4 (Elaboration) / - Prototype architectural critical components / - Finalize Basic Architecture
Sprint 5 (Construction) / - Implement core / - set up testing infrastructure
Sprint 6 (Construction) / - Implement & Test core concepts
Sprint 7 (Transition) / - Finalize Implementation / - Prepare Release Documents / - Prepare Presentation
Sprint 9 (Transition) / - Final Release / - Project Presentation

Project Management
Kickoff
Sprint Planning
Supervision Meeting
Retrospective

Milestones
End of Inception
Project Plan completed
Requirements completed
Basic architecture fixed
Architecture architecture fixed
End of Elaboration
Core functionality implemented
Basic functionality implemented
Documentation completed
Final Release / Sumbission

Documents
Project Plan
Abstract
Management Summary
Poster
Presentation
Final Submission Document

## Overview
Kickoff		Retrospective 1				Retrospective 2				Retrospective 3

Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5	Sprint 6	Sprint 7	Sprint 8	Sprint 9	Sprint 10	Sprint 11	Sprint 12	Sprint 13	Sprint 14
W38	W39	W40	W41	W42	W43	W44	W45	W46	W47	W48	W49	W50	W51

	project plan / completed				basic architecture / fixed				core functionality / Implemented					final release / / submission

			research completed / provisional technology fixed				architecture fixed / final technology fixed						documentation completed

												basic functionality implemented
						testing concept fixed

## Sprint Details
Sprint	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Tag	0.1.0	0.2.0	0.3.0	0.4.0
Date	19.09.2017-25.09.2017	26.09.2017-02.10.2017	03.10.2017-09.10.2017	10.10.2017-16.10.2017
Milestones	- project plan completed		- provisional technology fixed / - research completed
Time Budget	34	34	34	34
Tasks	- write project plan / - adapt Infrastructure	- academic research / - brainstorm basic concept / - define quality of service attributes / - retrospective 1 (at the end of the sprint)	- write basic concept (including testing concept) / - carry out language evaluation / - academic research	- draft basic architecture & domain model / - bootstrap project / - prototype architectural critical components
Documents / / Artefacts	- problem statement / - project plan draft	- first draft of concept paper / - project plan finalized	- research report / - language evaluation / - second draft of concept paper	- third draft of concept paper with drafted / architecture

Sprint	Sprint 5	Sprint 6	Sprint 7	Sprint 8
Tag	0.5.0	0.6.0	0.7.0	0.8.0
Date	17.10.2017-23.10.2017	24.10.2017-30.10.2017	31.10.2017-06.11.2017	07.11.2017-13.11.2017
Milestones	- basic architecture fixed	- testing concept fixed	- architecture fixed / - final technology fixed
Time Budget	34	34	34	34
Tasks	- prototype architectural critical components	- prototype testing architecture / - finalize testing concept / - retrospective 2 (at the end of the sprint)	- finalize architecture	- implement core functionality / - set up testing infrastructure
Documents / / Artefacts	- fourth draft of concept paper with / provisional architecture	- fifth draft of concept paper with final / testing concept	- concept paper

Sprint	Sprint 9	Sprint 10	Sprint 11	Sprint 12
Tag	0.9.0	0.10.0	0.11.0	0.12.0
Date	14.11.2017-20.11.2017	21.11.2017-27.11.2017	28.11.2017-04.12.2017	05.12.2017-11.12.2017
Milestones	- core functionality implemented			- basic functionality implemented
Time Budget	34	34	34	34
Tasks	- implement core functionality	- implement basic functionality / - retrospective 3 (at the end of the sprint)	- implement basic functionality / - exhaustive testing	- improve code quality & documentation / - exhaustive testing / - performance testing
Documents / / Artefacts

Sprint	Sprint 13	Sprint 14
Tag	0.13.0	0.14.0
Date	12.12.2017-18.12.2017	19.12.2017-22.12.2017
Milestones	- documentation completed	- final release / submission
Time Budget	34	34
Tasks	- finalize release documents / - prepare presentation	- prepare submission archive (e.g. JIRA export) / - print documents
Documents / / Artefacts	- management summary / - abstract / - poster / - final submission document / - presentation	- final submission archive (CD)

Total time budget: 476h + 2h for Kickoff (Before Sprint 1) + 2h Administration (vor SA)