## Sprint Details
Sprint	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Tag	0.1.0	0.2.0	0.3.0	0.4.0
Date	19.09.2017-25.09.2017	26.09.2017-02.10.2017	03.10.2017-09.10.2017	10.10.2017-16.10.2017
Milestones		- project plan completed	- provisional technology fixed / - research completed
Time Budget	34	34	34	34
Time Spent	32.5	27.25	29	63.75
Tasks	- write project plan / - adapt Infrastructure	- academic research / - brainstorm basic concept / - define quality of service attributes / - retrospective 1 (at the end of the sprint)	- write basic concept (including testing concept) / - carry out language evaluation / - academic research	- draft basic architecture & domain model / - bootstrap project / - prototype architectural critical components / - get familiar with Rust and its Network Stack
Documents / / Artefacts	- problem statement / - project plan draft	- first draft of concept paper / - project plan finalized	- research report / - language evaluation / - second draft of concept paper	- third draft of concept paper with drafted / architecture

Sprint	Sprint 5	Sprint 6	Sprint 7	Sprint 8
Tag	0.5.0	0.6.0	0.7.0	0.8.0
Date	17.10.2017-23.10.2017	24.10.2017-30.10.2017	31.10.2017-06.11.2017	07.11.2017-13.11.2017
Milestones	- basic architecture fixed	- testing concept fixed	- architecture fixed / - final technology fixed
Time Budget	34	34	34	34
Time Spent	55.45	19	43.25	40.75
Tasks	prototype architectural critical components	- prototype architectural critical components / - prototype testing architecture / - finalize testing concept / - retrospective 2 (Skipped)	- finalize architecture / - finalize testing concept / - implement core functionality	- implement core functionality / - set up testing infrastructure
Documents / / Artefacts	- fourth draft of concept paper with / provisional architecture	- fifth draft of concept paper with final / testing concept	- concept paper	- concept paper

Sprint	Sprint 9	Sprint 10	Sprint 11	Sprint 12
Tag	0.9.0	0.10.0	0.11.0	0.12.0
Date	14.11.2017-20.11.2017	21.11.2017-27.11.2017	28.11.2017-04.12.2017	05.12.2017-11.12.2017
Milestones	- core functionality implemented			- basic functionality implemented
Time Budget	34	34	34	34
Time Spent	33.25	29.25	28
Tasks	- implement core functionality	- implement basic functionality / - retrospective 3 (at the end of the sprint)	- implement basic functionality / - exhaustive testing	- improve code quality & documentation / - exhaustive testing / - performance testing / - begin with final submission document
Documents / / Artefacts

Sprint	Sprint 13	Sprint 14
Tag	0.13.0	0.14.0
Date	12.12.2017-18.12.2017	19.12.2017-22.12.2017
Milestones	- documentation completed	- final release / submission
Time Budget	34	34

Tasks	- finalize release documents / - prepare presentation	- prepare submission archive (e.g. JIRA export) / - print documents
Documents / / Artefacts	- management summary / - abstract / - final submission document / - poster / - presentation	- final submission archive (CD) / - poster

Total time budget: 476h + 2h for Kickoff (Before Sprint 1) + 2h Administration (vor SA)

## Evaluation
Sprint	Target	Actual	Difference
1	34	32.5	-1.5
2	34	27.25	-6.75
3	34	29	-5
4	34	63.75	29.75
5	34	55.45	21.45
6	34	19	-15
7	34	43.25	9.25
8	34	40.75	6.75
9	34	33.25	-0.75
10	34	29.25	-4.75
11	34	28	-6
12	34		-34
13	34		-34
14	34		-34
Total	476	401.45	-74.55